## Sheet1
System Name | Trucking Logistics Management System
Members: | Aves, Jake Hoker B. | [A]
| Kyono, Yoshinori Jr. L. | [B]
| Porcina, Andre L. | [C]
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1. Project Planning & Requirement Analysis
1.1: Define project scope and objectives |  | 2024-09-01 | 2024-09-07 | Done
1.2: Gather detailed requirements for each MVP |  | 2024-09-01 | 2024-09-07 | Done
1.3: Design the system architecture and database schema. |  | 2024-09-01 | 2024-09-07 | Todo
1.4: Assign teams and roles. |  | 2024-09-01 | 2024-09-07 | Todo
2. Core Infrastructure Setup |  |  |  | Todo
2.1: Set up development environment (version control, CI/CD, etc.). |  | 2024-09-08 | 2024-09-14 | Todo
2.2: Develop database structure to support customer, booking, and container data. |  | 2024-09-08 | 2024-09-14 | Todo
2.3: Create basic backend services for user authentication and authorization. |  | 2024-09-08 | 2024-09-14 | Todo
2.4: Begin implementing core API endpoints. |  | 2024-09-08 | 2024-09-14 | Todo
3. Customer Management System |  |  |  | Todo
3.1: Develop customer registration and CRUD operations. |  | 2024-09-15 | 2024-09-21 | Todo
3.2: Implement search and filter functionalities. |  | 2024-09-15 | 2024-09-21 | Todo
3.3: Integrate customer data with the database. |  | 2024-09-15 | 2024-09-21 | Todo
3.4: Conduct initial testing of customer management features. |  | 2024-09-15 | 2024-09-21 | Todo
4. Booking Management System |  |  |  | Todo
4.1: Develop booking creation form with customer assignment. |  | 2024-09-22 | 2024-09-30 | Todo
4.2: Implement container management within a booking. |  | 2024-09-22 | 2024-09-30 | Todo
4.3: Develop real-time progress tracking for each booking. |  | 2024-09-22 | 2024-09-30 | Todo
4.4: Integrate booking data with customer profiles. |  | 2024-09-22 | 2024-09-30 | Todo
5. Container Tracking System |  |  |  | Todo
5.1: Develop status update functionality for individual containers. |  | 2024-10-01 | 2024-10-07 | Todo
5.2: Link container statuses to overall booking status. |  | 2024-10-01 | 2024-10-07 | Todo
5.3: Implement historical tracking of container movements. |  | 2024-10-01 | 2024-10-07 | Todo
5.4: Integrate container tracking with the booking system. |  | 2024-10-01 | 2024-10-07 | Todo
6. Delivery Tracking and Documentation |  |  |  | Todo
6.1: Develop delivery input forms with detailed fields (e.g., vehicle details, route info). |  | 2024-10-08 | 2024-10-14 | Todo
6.2: Implement delivery status tracking (Loaded, Empty, etc.). |  | 2024-10-08 | 2024-10-14 | Todo
6.3: Add digital signature capture functionality. |  | 2024-10-08 | 2024-10-14 | Todo
6.4: Integrate delivery data with container and booking systems. |  | 2024-10-08 | 2024-10-14 | Todo
7. User Roles and Permissions Management |  |  |  | Todo
7.1: Develop role-based access control (RBAC) mechanisms. |  | 2024-10-15 | 2024-10-21 | Todo
7.2: Define and assign roles for drivers, office staff, and admins. |  | 2024-10-15 | 2024-10-21 | Todo
7.3: Implement secure access controls for different user levels. |  | 2024-10-15 | 2024-10-21 | Todo
7.4: Test and refine permissions to ensure correct access levels. |  | 2024-10-15 | 2024-10-21 | Todo
8. UI/UX Design and Final Integration |  |  |  | Todo
8.1: Finalize the user interface design for all modules. |  | 2024-10-22 | 2024-10-31 | Todo
8.2: Implement responsive design for both mobile and desktop use. |  | 2024-10-22 | 2024-10-31 | Todo
8.3: Conduct integration testing across all system components. |  | 2024-10-22 | 2024-10-31 | Todo
8.4: Perform user acceptance testing (UAT) and gather feedback. |  | 2024-10-22 | 2024-10-31 | Todo
8.5: Make necessary adjustments and finalize the system for deployment. |  | 2024-10-22 | 2024-10-31 | Todo